## Extended Lifecycle Comparison
Feature | Waterfall Model | V-Model | Spiral Model | Incremental Model | Agile - Scrum
Phases | Linear (Requirements, Design, Implementation, Testing, Maintenance) | Sequential, with Testing alongside Development | Iterative (Planning, Risk Analysis, Engineering, Evaluation) | Iterative (Design, Implementation, Testing in increments) | Iterative (Sprint Planning, Development, Review, Retrospective)
Flexibility | Low; changes are costly after requirements are defined | Low; changes are difficult after design phase | High; accommodates changes throughout | Moderate; changes can be accommodated between increments | High; accommodates changes after each sprint
Risk Management | Minimal; risks are identified at the beginning | Minimal; risks are considered during the development phase | Continuous; risks are assessed at each spiral iteration | Moderate; risk assessment occurs during each increment | Continuous; risks are assessed in each sprint
Customer Involvement | Low; customer feedback is mostly at the end | Low; customer involvement is limited to requirements gathering | Moderate; customer feedback is solicited at each iteration | Moderate; customer involvement in each increment | High; customer is involved in every sprint
Best Use Case | Simple projects with well-defined requirements | Projects requiring high reliability and testing | Large and complex projects with high risk | Projects with evolving requirements | Dynamic projects requiring frequent changes and customer collaboration
Documentation | Extensive; documentation at every phase | Extensive; documentation for both development and testing | Moderate; documentation is less formal, focusing on risk management | Moderate; documentation focused on each increment | Minimal; emphasizes working software over comprehensive documentation
Development Approach | Sequential | Sequential with validation at each stage | Iterative, focusing on risk and feedback | Incremental, focusing on building small parts | Incremental and iterative, focusing on deliverables every sprint
Approach to Testing | Testing is a separate phase after development | Testing is integrated with development phases | Testing occurs in each iteration with risk assessments | Testing is performed for each increment | Testing is continuous throughout each sprint, with frequent reviews and adjustments
Risk Assessment | Minimal risk assessment after the design phase | Risk assessment is done alongside validation | Extensive risk analysis in every iteration | Risk assessment for each increment | Risk is reviewed and addressed in every sprint
Project Type/Capability | Suited for well-defined, low-complexity projects | High-capability, safety-critical projects | Suitable for large, high-risk projects | Best for medium-complexity projects with evolving features | Best for high-capability, rapidly evolving projects
Resources | Requires significant resources in later stages | Requires substantial testing resources | Requires significant resources for continuous assessment | Resource-efficient; incremental approach reduces initial overhead | Lightweight on resources; focused on small, cross-functional teams
Planning | Extensive up-front planning | Detailed and structured planning process | Iterative planning with regular updates | Incremental planning, adjusting after each iteration | Iterative planning in sprints, adapting as needed
Requirements Specification | Rigid requirements; must be fully specified before development | Must be fully specified at the start | Can be flexible and evolve over time | Requirements can be redefined in each increment | Requirements evolve throughout the project
Ease of Use | Complex; follows a rigid sequence of phases | Moderate; integrates testing with each phase | Moderate; adapts to changes and feedback | Moderate; adds flexibility between increments | Easy to use due to adaptability and frequent customer feedback
Bug Fixing Approach | Bugs are typically addressed after the entire system is built | Bugs are found and fixed during validation phases | Bugs are found and addressed in each iteration | Bugs are fixed incrementally in each cycle | Bugs are addressed immediately in each sprint
Maintaining/Evolution of Software | Maintaining is challenging due to sequential structure | Maintaining is easier due to validation structure | Flexible, maintains adaptability over project lifecycle | Evolution is manageable due to the incremental approach | Maintaining and evolving are part of each sprint cycle
Example | Traditional software applications | Safety-critical systems (e.g., medical software) | Large-scale applications (e.g., military software) | Web applications or software requiring frequent updates | Product development, mobile applications, and software with evolving needs